PM Knowledge Hub AI

Learning Curriculum Blueprint

Version 1.0  ·  June 2026  ·  30 Learning Experiences  ·  5 Tracks

THIS DOCUMENT IS The complete implementation blueprint for PM Hub AI's educational content. It defines 30 learning experiences across 5 tracks — each with a learning objective, activity pattern, expected outcome, interview alignment, and implementation priority. It is not a content library. It is the instructional design backbone of a personal PM mentor.

# 1. Curriculum Overview

The PM Hub AI curriculum is organized into 5 learning tracks, progressing from foundational PM concepts to advanced and emerging topics. Tracks are independent — learners may follow the recommended order or enter at the track that matches their current level.

|  | Track | Level | Experiences | Total Time | P1 | P2 | P3 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 🏗️ | Project Fundamentals | Beginner | 6 | 49 min | 5 | 1 | 0 |
| ⚡ | Agile & Scrum | Beginner–Intermediate | 7 | 60 min | 5 | 1 | 1 |
| 🤝 | Stakeholder Management | Intermediate | 6 | 54 min | 3 | 2 | 1 |
| ⚠️ | Risk Management | Intermediate | 6 | 51 min | 3 | 2 | 1 |
| 🤖 | AI for PMs | Intermediate–Advanced | 5 | 42 min | 3 | 1 | 1 |
|  | TOTAL |  | 30 | ~4.2 hrs | 19 | 7 | 4 |

Priority 1 experiences form the MVP — 19 experiences covering all five tracks. Priority 2 adds depth and reinforcement. Priority 3 delivers interview capstones for learners targeting specific PM roles.

# Track 1: 🏗️ Project Fundamentals

| Level | Beginner |
| --- | --- |
| Total Time | 6 experiences · 49 min |
| Purpose | Every PM career starts here. This track builds the conceptual foundation that every other track depends on. Without a clear understanding of what projects are, how they are structured, and what PMs do, every advanced concept becomes harder to learn. |

| T1-01 What Is a Project? P1 — ESSENTIAL (MVP) Beginner · 7 min · Pattern A — Concept Introduction |
| --- |
| Objective | Distinguish projects from ongoing operations and identify the three defining characteristics of a project. |
| PM Concept | Project definition, temporary endeavor, unique outcome, progressive elaboration, project vs. operations. |
| Activities | Short Reading → Matching (project vs. operation examples) → Multiple Choice Quiz → Key Takeaway |
| Outcome | Given any business activity, the learner can correctly classify it as a project or an operation and explain why. |
| Interview ▸ | Interviewers test this to verify foundational PM vocabulary and conceptual clarity. |
| Q: What is the difference between a project and business-as-usual? Q: Can you give an example of something that looks like a project but isn't? Q: What makes a project temporary? |

| T1-02 The Project Lifecycle P1 — ESSENTIAL (MVP) Beginner · 8 min · Pattern B — Process Teaching |
| --- |
| Objective | Navigate the five project phases and identify which activities belong in each phase. |
| PM Concept | Initiation, Planning, Execution, Monitoring & Control, Closure — PMBOK lifecycle phases. |
| Activities | Short Reading → Process Builder (arrange phases and key activities) → Scenario Analysis (identify which phase a project crisis belongs to) → Key Takeaway |
| Outcome | Given any project scenario, the learner can identify the current phase and name the two most critical actions for that phase. |
| Interview ▸ | Interviewers use this to assess whether the candidate has a structured mental model for project delivery. |
| Q: Walk me through how you approach a new project from scratch. Q: What do you do during project initiation? Q: How do you know a project is ready to close? |

| T1-03 The Triple Constraint P1 — ESSENTIAL (MVP) Beginner · 8 min · Pattern C — PM Judgment |
| --- |
| Objective | Make and communicate scope/time/cost trade-off decisions under stakeholder pressure. |
| PM Concept | Iron triangle, scope-time-cost interdependence, trade-off communication, quality as the fourth dimension. |
| Activities | Short Reading → Decision Making Scenario (client demands 2-week earlier delivery at same cost) → Key Takeaway → Reflection (describe a real or imagined trade-off decision) |
| Outcome | The learner can propose a trade-off solution, quantify its impact, and communicate it to a stakeholder diplomatically. |
| Interview ▸ | Classic PM interview territory. Interviewers test whether candidates understand that you cannot change one constraint without affecting others. |
| Q: A client asks you to deliver the project 2 weeks early without extra budget. What do you do? Q: What is the triple constraint? Q: How do you handle scope creep? |

| T1-04 The Project Charter P1 — ESSENTIAL (MVP) Beginner · 7 min · Pattern B — Process Teaching |
| --- |
| Objective | Create and explain every section of a project charter and understand the authority it grants. |
| PM Concept | Charter purpose, components (objectives, scope, stakeholders, PM authority, budget), sign-off, kickoff. |
| Activities | Short Reading → Process Builder (assemble charter sections in logical order) → Multiple Choice Quiz → Key Takeaway |
| Outcome | The learner can list all major charter sections, explain why each matters, and describe what formal authority the charter provides to the PM. |
| Interview ▸ | Often tested as 'How do you start a project?' — interviewers want to see structured thinking from day one. |
| Q: What documents do you create at the start of a project? Q: What is a project charter and what does it grant you? Q: Who should sign a project charter and why? |

| T1-05 The PM Role in Practice P1 — ESSENTIAL (MVP) Beginner · 9 min · Pattern C — PM Judgment |
| --- |
| Objective | Describe the real day-to-day responsibilities of a PM and demonstrate sound judgment in common PM situations. |
| PM Concept | PM responsibilities, soft skills, facilitation, communication, accountability, blocker management. |
| Activities | Short Reading → Decision Scenario (developer reports a blocker during sprint) → Communication Challenge (communicate a project delay to a client) → Reflection |
| Outcome | The learner can articulate what PMs actually do (beyond 'making plans'), handle a team blocker situation, and draft a professional delay notification. |
| Interview ▸ | 'Tell me about your day-to-day as a PM' is one of the most common interview questions. This experience prepares a structured, honest answer. |
| Q: What does a PM actually do? Q: How do you handle blockers? Q: Describe a time you had to deliver bad news to a client. |

| T1-06 Fundamentals Review & Interview Prep P2 — IMPORTANT Beginner · 10 min · Pattern E — Deep Reinforcement |
| --- |
| Objective | Consolidate all Track 1 knowledge and articulate PM fundamentals confidently in an interview. |
| PM Concept | All Track 1 concepts: project definition, lifecycle, triple constraint, charter, PM role. |
| Activities | Flashcards (8 key terms) → Scenario Analysis (end-to-end project situation requiring lifecycle + constraint decisions) → Communication Challenge (answer 'Tell me about yourself as a PM' in 90 seconds) |
| Outcome | The learner can answer all core PM fundamentals questions with structured, specific, confident responses. |
| Interview ▸ | Capstone for the full track — synthesizes all concepts into interview-ready answers. |
| Q: Tell me about yourself as a PM. Q: What makes a great Project Manager? Q: What would you do in your first 30 days as PM on a new project? |

# Track 2: ⚡ Agile & Scrum

| Level | Beginner – Intermediate |
| --- | --- |
| Total Time | 7 experiences · 60 min |
| Purpose | The most requested PM skill set in the current job market. This track goes beyond memorizing Scrum terms — it builds the ability to run sprints, manage backlogs, read metrics, and make Agile decisions under pressure. |

| T2-01 Waterfall vs. Agile P1 — ESSENTIAL (MVP) Beginner · 7 min · Pattern C — PM Judgment |
| --- |
| Objective | Select the right delivery methodology for a given project context and justify the choice. |
| PM Concept | Waterfall (predictive), Agile (adaptive), hybrid, when each is appropriate, trade-offs. |
| Activities | Short Reading → Decision Scenario (choose methodology for 3 different project types) → Matching (project characteristics to methodology) → Key Takeaway |
| Outcome | Given a project brief, the learner can recommend Waterfall, Agile, or Hybrid and provide a clear, defensible rationale. |
| Interview ▸ | Nearly universal in technical PM interviews — interviewers want to see contextual judgment, not religious preference for one method. |
| Q: When would you choose Waterfall over Agile? Q: Can you use Agile for projects with a fixed regulatory deadline? Q: What is a hybrid approach? |

| T2-02 The Scrum Framework P1 — ESSENTIAL (MVP) Beginner · 9 min · Pattern B — Process Teaching |
| --- |
| Objective | Explain Scrum's three roles, five events, and three artifacts and know who is responsible for each. |
| PM Concept | Product Owner, Scrum Master, Dev Team, Sprint, Backlog, Sprint Review, Retrospective, Increment. |
| Activities | Short Reading → Matching (roles → responsibilities, artifacts → owners) → Process Builder (arrange Scrum events in correct sprint sequence) → Multiple Choice Quiz |
| Outcome | The learner can diagram the Scrum framework from memory and explain what happens in every event and who makes each decision. |
| Interview ▸ | The most tested Agile topic. Interviewers assess depth — many candidates memorize terms but cannot explain who decides what. |
| Q: What is the difference between a Scrum Master and a Product Owner? Q: Who can add items to the sprint backlog? Q: What is the purpose of a Sprint Retrospective vs. a Sprint Review? |

| T2-03 Writing Great User Stories P1 — ESSENTIAL (MVP) Beginner · 8 min · Pattern D — Skill Practice |
| --- |
| Objective | Write well-formed user stories using the INVEST criteria and evaluate the quality of existing stories. |
| PM Concept | As-a / I-want / So-that format, acceptance criteria, INVEST (Independent, Negotiable, Valuable, Estimable, Small, Testable). |
| Activities | Short Reading → Worked Example (analyze 2 good and 2 poor user stories) → Drag & Drop (sort 8 stories by quality score) → Key Takeaway |
| Outcome | The learner can write a user story from a business requirement and critique any given story using the INVEST criteria. |
| Interview ▸ | Tested in Agile PM and product interviews. Interviewers look for understanding of value, not just format. |
| Q: Write a user story for a login feature. Q: What makes a user story 'ready'? Q: What is a spike and when would you use one? |

| T2-04 Backlog Prioritization P1 — ESSENTIAL (MVP) Intermediate · 9 min · Pattern D — Skill Practice |
| --- |
| Objective | Prioritize a product backlog using MoSCoW and WSJF and defend the order against stakeholder pushback. |
| PM Concept | MoSCoW (Must/Should/Could/Won't), WSJF (Weighted Shortest Job First), value vs. effort, stakeholder negotiation. |
| Activities | Short Reading → Prioritization Exercise (rank 10 backlog items using MoSCoW) → Decision Scenario (VP challenges the priority order — respond diplomatically) → Key Takeaway |
| Outcome | The learner can apply MoSCoW or WSJF to any backlog, explain the reasoning, and negotiate priority changes with data. |
| Interview ▸ | Critical for Technical PM and Product Owner roles. Interviewers test whether candidates can make and defend hard trade-off decisions. |
| Q: How do you decide what to build first? Q: A senior stakeholder wants to move their feature to the top of the backlog. What do you do? Q: What is WSJF? |

| T2-05 Running a Sprint P1 — ESSENTIAL (MVP) Intermediate · 10 min · Pattern B — Process Teaching |
| --- |
| Objective | Plan and manage a complete sprint cycle including recovery from mid-sprint complications. |
| PM Concept | Sprint planning capacity, velocity, daily standup anti-patterns, sprint review facilitation, retrospective techniques. |
| Activities | Short Reading → Sprint Planning Exercise (allocate 12 stories across 2-week sprint given team velocity) → Scenario Analysis (burndown shows sprint at risk on day 7 — decide and act) → Key Takeaway |
| Outcome | The learner can facilitate sprint planning, read a burndown chart, and make a mid-sprint correction decision with confidence. |
| Interview ▸ | Interviewers want to see hands-on Scrum experience. Operational depth separates real practitioners from certificate holders. |
| Q: How do you plan a sprint? Q: Your sprint is 50% through and you're at 20% completion. What do you do? Q: What makes a daily standup effective vs. ineffective? |

| T2-06 Agile Metrics That Matter P2 — IMPORTANT Intermediate · 7 min · Pattern A — Concept Introduction |
| --- |
| Objective | Read and interpret Agile metrics (velocity, burndown, cycle time) and translate them into decisions. |
| PM Concept | Velocity, sprint burndown, release burnup, cycle time, throughput, team health metrics. |
| Activities | Short Reading → Multiple Choice Quiz (what does this burndown pattern mean?) → Decision Scenario (metrics show declining velocity — investigate and respond) → Key Takeaway |
| Outcome | The learner can look at an Agile dashboard, identify what is healthy vs. concerning, and name the specific action each metric calls for. |
| Interview ▸ | Metrics questions reveal whether a candidate actually ran sprints or just observed them. |
| Q: How do you track progress in Agile? Q: What does a flat burndown chart tell you? Q: How do you forecast delivery date using velocity? |

| T2-07 Agile Interview Masterclass P3 — NICE TO HAVE Intermediate · 10 min · Pattern E — Deep Reinforcement |
| --- |
| Objective | Answer any Agile interview question with structured, experience-based responses. |
| PM Concept | All Track 2 concepts + STAR method application to Agile scenarios. |
| Activities | Flashcards (10 Agile terms) → Communication Challenge (answer 'How does your team handle scope changes in Agile?') → Scenario Analysis (complex Agile failure — what went wrong and what would you do differently?) |
| Outcome | The learner can deliver complete, structured, specific answers to any standard Agile interview question. |
| Interview ▸ | Full capstone for Agile knowledge — prepares for both behavioral and technical Agile questions. |
| Q: Describe a failed sprint and what you learned from it. Q: How do you handle a team member who refuses to follow Scrum? Q: What certifications do you have and what do they not teach you? |

# Track 3: 🤝 Stakeholder Management

| Level | Intermediate |
| --- | --- |
| Total Time | 6 experiences · 54 min |
| Purpose | The skill that separates good PMs from great ones. Projects rarely fail because of technical problems — they fail because of people problems. This track develops the judgment, communication skill, and political awareness needed to manage complex stakeholder environments. |

| T3-01 Identifying Stakeholders P1 — ESSENTIAL (MVP) Intermediate · 7 min · Pattern D — Skill Practice |
| --- |
| Objective | Systematically identify all project stakeholders, including non-obvious ones, and document them. |
| PM Concept | Stakeholder definition, stakeholder register, internal vs. external, primary vs. secondary stakeholders. |
| Activities | Short Reading → Drag & Drop (sort 12 people/groups into stakeholder categories) → Multiple Choice Quiz → Key Takeaway |
| Outcome | Given any project type, the learner can build a complete stakeholder list, categorize each stakeholder, and create a basic stakeholder register. |
| Interview ▸ | Interviewers test whether candidates think beyond the obvious sponsor and team — lateral thinking about impact and influence is key. |
| Q: Who are the stakeholders on a software project? Q: How do you identify stakeholders you might have missed? Q: What is a stakeholder register? |

| T3-02 Power & Interest Analysis P1 — ESSENTIAL (MVP) Intermediate · 9 min · Pattern D — Skill Practice |
| --- |
| Objective | Map stakeholders on the power/interest grid and define the right engagement strategy for each quadrant. |
| PM Concept | Power/Interest matrix, four quadrants (manage closely, keep informed, keep satisfied, monitor), engagement levels. |
| Activities | Short Reading → Stakeholder Mapping Exercise (place 8 stakeholders on the grid for a given project) → Decision Scenario (key stakeholder moves from 'keep informed' to 'manage closely' — what changes?) → Key Takeaway |
| Outcome | The learner can place any stakeholder on the power/interest grid and describe a specific engagement approach for each quadrant. |
| Interview ▸ | Demonstrates structured stakeholder thinking — expected at mid-to-senior PM level interviews. |
| Q: How do you prioritize which stakeholders to spend time with? Q: Describe the power/interest matrix and how you use it. Q: How would your strategy change if a passive stakeholder suddenly became highly engaged? |

| T3-03 Stakeholder Communication Planning P1 — ESSENTIAL (MVP) Intermediate · 9 min · Pattern D — Skill Practice |
| --- |
| Objective | Design a communication plan and adapt message tone for different stakeholders. |
| PM Concept | Communication plan components (who, what, how often, format), audience analysis, tone calibration. |
| Activities | Short Reading → Process Builder (build a communication plan from components) → Communication Challenge (write a status update for an anxious sponsor vs. a technical lead) → Key Takeaway |
| Outcome | The learner can create a communication plan and write two versions of the same message adapted for different audiences. |
| Interview ▸ | Interviewers assess whether candidates can communicate strategically, not just broadcast information. |
| Q: How do you keep stakeholders informed without overloading them? Q: How do you tailor communication to an executive vs. a developer? Q: What is in a communication management plan? |

| T3-04 Managing Difficult Stakeholders P2 — IMPORTANT Intermediate · 10 min · Pattern C — PM Judgment |
| --- |
| Objective | Choose and apply the right influence or escalation strategy for resistant, demanding, or disengaged stakeholders. |
| PM Concept | Resistance, disengagement, scope demands, influence strategies, escalation paths, conflict resolution. |
| Activities | Short Reading → Decision Scenario (executive sponsor stops attending project reviews — what do you do?) → Decision Scenario (stakeholder repeatedly demands out-of-scope features — three options, choose and explain) → Reflection |
| Outcome | The learner can identify the underlying cause of stakeholder resistance and select a proportionate, professional response strategy. |
| Interview ▸ | Behavioral interview territory — interviewers want specific STAR stories about difficult stakeholder situations. |
| Q: Tell me about a time you had a difficult stakeholder. What did you do? Q: How do you manage a stakeholder who keeps requesting scope changes? Q: How do you escalate a stakeholder conflict? |

| T3-05 Managing Up — Executive Communication P2 — IMPORTANT Advanced · 9 min · Pattern C — PM Judgment |
| --- |
| Objective | Communicate risks, bad news, and decisions to senior leadership in a way that builds confidence, not alarm. |
| PM Concept | Executive communication principles, BLUF (Bottom Line Up Front), solution-first framing, risk escalation. |
| Activities | Short Reading → Communication Challenge (escalate a critical risk to a VP in 3 sentences) → Communication Challenge (present a project delay in a board update without losing credibility) → Key Takeaway |
| Outcome | The learner can draft executive communications that are concise, solution-oriented, and appropriately risk-transparent. |
| Interview ▸ | Separates mid-level PMs from senior PMs. The ability to communicate upward without creating panic is a senior skill. |
| Q: How do you deliver bad news to an executive? Q: A project is 2 weeks late. How do you tell the CTO? Q: What is BLUF and why does it matter? |

| T3-06 Stakeholder Management Masterclass P3 — NICE TO HAVE Advanced · 10 min · Pattern E — Deep Reinforcement |
| --- |
| Objective | Demonstrate stakeholder management expertise across all scenarios and interview question types. |
| PM Concept | All Track 3 concepts + STAR method for stakeholder behavioral questions. |
| Activities | Flashcards (8 key terms and frameworks) → Scenario Analysis (multi-stakeholder conflict — 3 competing interests, limited PM authority) → Communication Challenge (craft a message that satisfies two opposing stakeholders simultaneously) |
| Outcome | The learner can answer any stakeholder management interview question with a specific, structured example and clear reasoning. |
| Interview ▸ | Full capstone — targets behavioral and situational questions at the senior PM level. |
| Q: Describe a situation where you had competing stakeholder priorities. How did you resolve it? Q: Tell me about a time you changed a stakeholder's position. Q: How do you build trust with a stakeholder who is skeptical of the project? |

# Track 4: ⚠️ Risk Management

| Level | Intermediate |
| --- | --- |
| Total Time | 6 experiences · 51 min |
| Purpose | Proactive risk management is a senior PM differentiator. This track teaches learners to identify risks before they become issues, assess them with data, respond with appropriate strategies, and communicate risk status to leadership. |

| T4-01 Understanding Risk P1 — ESSENTIAL (MVP) Intermediate · 7 min · Pattern A — Concept Introduction |
| --- |
| Objective | Distinguish risk from issue, classify risks by category, and explain why proactive risk management matters. |
| PM Concept | Risk definition, risk vs. issue, risk categories (technical, external, organizational, PM), positive vs. negative risk. |
| Activities | Short Reading → Matching (risk or issue? + classify into categories) → Multiple Choice Quiz → Key Takeaway |
| Outcome | The learner can categorize any project risk, distinguish it from an active issue, and explain the cost of ignoring it. |
| Interview ▸ | Foundational risk vocabulary — tested to assess whether candidates manage risk reactively or proactively. |
| Q: What is the difference between a risk and an issue? Q: Can risks be positive? Give an example. Q: What are the main categories of project risk? |

| T4-02 Risk Identification P1 — ESSENTIAL (MVP) Intermediate · 8 min · Pattern D — Skill Practice |
| --- |
| Objective | Lead a structured risk identification session and build a preliminary risk list. |
| PM Concept | Brainstorming, SWOT analysis, assumption analysis, expert judgment, risk breakdown structure. |
| Activities | Short Reading → Brainstorm Exercise (identify risks in a given project scenario using 3 techniques) → Drag & Drop (sort 12 items as risk, issue, or assumption) → Key Takeaway |
| Outcome | The learner can facilitate a risk identification session and produce a preliminary risk list organized by category. |
| Interview ▸ | Interviewers test whether candidates have a repeatable process for risk identification, not just intuition. |
| Q: How do you identify risks at the start of a project? Q: What techniques do you use for risk identification? Q: How do you turn project assumptions into risk items? |

| T4-03 Risk Assessment & Prioritization P1 — ESSENTIAL (MVP) Intermediate · 9 min · Pattern D — Skill Practice |
| --- |
| Objective | Score, prioritize, and explain risk priorities using a probability × impact matrix. |
| PM Concept | Probability/impact matrix, risk score, risk threshold, risk tolerance, qualitative vs. quantitative assessment. |
| Activities | Short Reading → Risk Classification Exercise (place 10 project risks on a P×I matrix and assign priority) → Decision Scenario (two high-scored risks, limited mitigation budget — which do you address first and why?) → Key Takeaway |
| Outcome | The learner can score any risk on a probability/impact matrix and make a data-supported prioritization decision. |
| Interview ▸ | Demonstrates analytical risk thinking — interviewers look for a structured approach, not gut feeling. |
| Q: How do you assess a risk once you've identified it? Q: Two risks have the same score — how do you decide which to address first? Q: What is a risk threshold? |

| T4-04 Risk Response Strategies P2 — IMPORTANT Intermediate · 8 min · Pattern A — Concept Introduction |
| --- |
| Objective | Select and apply the right risk response (Avoid, Transfer, Mitigate, Accept, Exploit) for any given risk. |
| PM Concept | Negative risk responses: Avoid, Transfer, Mitigate, Accept. Positive risk responses: Exploit, Enhance, Share, Accept. |
| Activities | Short Reading → Matching (risk scenario → best response strategy) → Decision Scenario (3 realistic project risks — choose response and draft the action) → Key Takeaway |
| Outcome | The learner can select and justify the optimal response strategy for any risk type and describe a concrete action plan for each response. |
| Interview ▸ | Tests depth — many candidates know the terms but cannot explain when Mitigate is better than Transfer. |
| Q: What are the four risk response strategies? Q: When would you transfer a risk vs. mitigate it? Q: Give an example of a risk you would accept. |

| T4-05 Building a Risk Register P2 — IMPORTANT Intermediate · 9 min · Pattern B — Process Teaching |
| --- |
| Objective | Create, populate, and maintain a risk register throughout a project lifecycle. |
| PM Concept | Risk register fields (ID, description, category, probability, impact, score, owner, response, status), review cadence. |
| Activities | Short Reading → Process Builder (assemble a risk register from component fields — in logical order) → Scenario Analysis (risk materialized mid-project — update the register and communicate) → Key Takeaway |
| Outcome | The learner can create a project risk register and describe exactly how and when to update it across the project lifecycle. |
| Interview ▸ | Practical artifact knowledge — interviewers may ask to see or describe a real risk register from past projects. |
| Q: Walk me through a risk register you have used. Q: How often do you review the risk register? Q: What happens when a risk becomes an issue? |

| T4-06 Risk Management Masterclass P3 — NICE TO HAVE Advanced · 10 min · Pattern E — Deep Reinforcement |
| --- |
| Objective | Demonstrate risk management expertise in behavioral and scenario-based interview questions. |
| PM Concept | All Track 4 concepts + real-world risk management under pressure. |
| Activities | Flashcards (10 risk terms) → Decision Scenario (critical technical risk surfaces in sprint 3 of a fixed-deadline project) → Communication Challenge (communicate the risk to a sponsor who doesn't want bad news) |
| Outcome | The learner can describe a complete risk management approach from identification to response, using specific examples, in an interview setting. |
| Interview ▸ | Senior PM capstone — targets questions about risk leadership under pressure. |
| Q: Tell me about a risk that materialized. How did you manage it? Q: How do you get a team to take risk management seriously? Q: Describe your approach to risk management on a project you led. |

# Track 5: 🤖 AI for PMs

| Level | Intermediate – Advanced |
| --- | --- |
| Total Time | 5 experiences · 42 min |
| Purpose | The emerging competency that defines the next generation of PMs. This track covers what PMs need to know about AI — not to build models, but to lead AI projects, use AI tools, manage AI risks, and position themselves as AI-fluent leaders. |

| T5-01 AI Fundamentals for PMs P1 — ESSENTIAL (MVP) Intermediate · 7 min · Pattern A — Concept Introduction |
| --- |
| Objective | Explain AI/ML concepts accurately to stakeholders and identify when AI is relevant to a project. |
| PM Concept | AI vs. ML vs. GenAI, LLMs, training data, model, inference, hallucination, AI project vs. AI-assisted project. |
| Activities | Short Reading → Matching (AI terms → PM-relevant plain-English definitions) → Multiple Choice Quiz (is this an AI project or not?) → Key Takeaway |
| Outcome | The learner can explain 8 core AI terms in plain language and identify whether a given initiative is an AI project, an AI-assisted project, or neither. |
| Interview ▸ | AI PM roles are growing rapidly. Interviewers test conceptual fluency — you don't need to build models, but you must understand them. |
| Q: What is the difference between AI and ML? Q: What is a hallucination in the context of an LLM? Q: How do you manage a project where the output is a trained model? |

| T5-02 AI Tools in PM Practice P1 — ESSENTIAL (MVP) Intermediate · 8 min · Pattern D — Skill Practice |
| --- |
| Objective | Identify 5+ PM tasks where AI tools add value and use them responsibly within project constraints. |
| PM Concept | AI-assisted writing, meeting summarization, risk brainstorming with AI, AI for reporting, limitations and risks of AI use. |
| Activities | Short Reading → Scenario Analysis (choose the right AI tool for each PM task from a menu of 6) → Reflection (which AI tool would save you the most time in your current or most recent role, and what is the risk of using it?) |
| Outcome | The learner can describe 5 specific PM use cases for AI tools, the benefit of each, and the guardrails needed for responsible use. |
| Interview ▸ | 'How do you use AI in your work?' is now a standard screening question. Vague answers fail — specific use cases impress. |
| Q: How do you use AI in your day-to-day PM work? Q: What are the risks of using AI-generated content in project documentation? Q: How do you verify AI output before sharing it with stakeholders? |

| T5-03 Managing AI/ML Projects P1 — ESSENTIAL (MVP) Intermediate · 9 min · Pattern C — PM Judgment |
| --- |
| Objective | Apply and adapt standard PM practices to the unique delivery challenges of AI/ML projects. |
| PM Concept | Data dependencies, model iteration cycles, experiment tracking, non-deterministic delivery, AI-specific risks. |
| Activities | Short Reading → Decision Scenario (AI model underperforms in production — PM response options) → Risk Classification (classify 8 AI-specific project risks on the P×I matrix) → Key Takeaway |
| Outcome | The learner can describe 5 ways AI/ML projects differ from standard software projects and adapt their PM approach accordingly. |
| Interview ▸ | The core competency test for AI PM roles — interviewers need to know you understand what makes AI delivery different. |
| Q: How does managing an AI project differ from a standard software project? Q: How do you define 'done' when the output is a machine learning model? Q: How do you handle a project where the data isn't ready? |

| T5-04 Ethical AI in Projects P2 — IMPORTANT Advanced · 8 min · Pattern C — PM Judgment |
| --- |
| Objective | Identify ethical risks in AI projects and escalate them appropriately as a PM. |
| PM Concept | Bias, fairness, transparency, accountability, privacy, AI regulation (GDPR, EU AI Act), PM's ethical responsibility. |
| Activities | Short Reading → Decision Scenario (team discovers model bias affecting a protected group during testing — three response options) → Reflection (what is the PM's responsibility when the team identifies an ethical concern the business wants to ignore?) |
| Outcome | The learner can identify at least 4 categories of AI ethical risk and describe how to escalate an ethical concern through a project governance structure. |
| Interview ▸ | Senior AI PM differentiator — demonstrates awareness of real-world AI governance and the PM's accountability beyond delivery. |
| Q: What is algorithmic bias and how would you detect it on a project? Q: What would you do if you discovered the AI system your team built was producing unfair outcomes? Q: What regulations apply to AI projects in your industry? |

| T5-05 AI PM Interview Masterclass P3 — NICE TO HAVE Advanced · 10 min · Pattern E — Deep Reinforcement |
| --- |
| Objective | Position confidently as an AI-fluent PM in both technical and behavioral interview questions. |
| PM Concept | All Track 5 concepts + AI PM career positioning + synthesis. |
| Activities | Flashcards (12 AI PM terms) → Communication Challenge (explain what an LLM does to a non-technical CFO in 60 seconds) → Scenario Analysis (AI project in delivery crisis — prioritize and respond) |
| Outcome | The learner can answer 'How do you manage AI projects?' with depth, specificity, and structured reasoning — and explain AI concepts to any audience. |
| Interview ▸ | Capstone for AI PM credibility — combines technical fluency, delivery experience, and communication skill. |
| Q: What is your experience with AI projects? Q: How do you keep up with AI developments as a PM? Q: How would you build an AI team if you were starting from scratch? |

# Priority Implementation Backlog

This table is the development backlog for the educational content team. Build Priority 1 first. Do not begin Priority 2 until all Priority 1 experiences are implemented and tested with real learners.

P1 — ESSENTIAL (MVP) — 19 experiences

| ID | Title | Pattern | Duration | Track |
| --- | --- | --- | --- | --- |
| T1-01 | What Is a Project? | Pattern A — Concept Introduction | 7 min | T1 |
| T1-02 | The Project Lifecycle | Pattern B — Process Teaching | 8 min | T1 |
| T1-03 | The Triple Constraint | Pattern C — PM Judgment | 8 min | T1 |
| T1-04 | The Project Charter | Pattern B — Process Teaching | 7 min | T1 |
| T1-05 | The PM Role in Practice | Pattern C — PM Judgment | 9 min | T1 |
| T2-01 | Waterfall vs. Agile | Pattern C — PM Judgment | 7 min | T2 |
| T2-02 | The Scrum Framework | Pattern B — Process Teaching | 9 min | T2 |
| T2-03 | Writing Great User Stories | Pattern D — Skill Practice | 8 min | T2 |
| T2-04 | Backlog Prioritization | Pattern D — Skill Practice | 9 min | T2 |
| T2-05 | Running a Sprint | Pattern B — Process Teaching | 10 min | T2 |
| T3-01 | Identifying Stakeholders | Pattern D — Skill Practice | 7 min | T3 |
| T3-02 | Power & Interest Analysis | Pattern D — Skill Practice | 9 min | T3 |
| T3-03 | Stakeholder Communication Planning | Pattern D — Skill Practice | 9 min | T3 |
| T4-01 | Understanding Risk | Pattern A — Concept Introduction | 7 min | T4 |
| T4-02 | Risk Identification | Pattern D — Skill Practice | 8 min | T4 |
| T4-03 | Risk Assessment & Prioritization | Pattern D — Skill Practice | 9 min | T4 |
| T5-01 | AI Fundamentals for PMs | Pattern A — Concept Introduction | 7 min | T5 |
| T5-02 | AI Tools in PM Practice | Pattern D — Skill Practice | 8 min | T5 |
| T5-03 | Managing AI/ML Projects | Pattern C — PM Judgment | 9 min | T5 |

P2 — IMPORTANT — 7 experiences

| ID | Title | Pattern | Duration | Track |
| --- | --- | --- | --- | --- |
| T1-06 | Fundamentals Review & Interview Prep | Pattern E — Deep Reinforcement | 10 min | T1 |
| T2-06 | Agile Metrics That Matter | Pattern A — Concept Introduction | 7 min | T2 |
| T3-04 | Managing Difficult Stakeholders | Pattern C — PM Judgment | 10 min | T3 |
| T3-05 | Managing Up — Executive Communication | Pattern C — PM Judgment | 9 min | T3 |
| T4-04 | Risk Response Strategies | Pattern A — Concept Introduction | 8 min | T4 |
| T4-05 | Building a Risk Register | Pattern B — Process Teaching | 9 min | T4 |
| T5-04 | Ethical AI in Projects | Pattern C — PM Judgment | 8 min | T5 |

P3 — NICE TO HAVE — 4 experiences

| ID | Title | Pattern | Duration | Track |
| --- | --- | --- | --- | --- |
| T2-07 | Agile Interview Masterclass | Pattern E — Deep Reinforcement | 10 min | T2 |
| T3-06 | Stakeholder Management Masterclass | Pattern E — Deep Reinforcement | 10 min | T3 |
| T4-06 | Risk Management Masterclass | Pattern E — Deep Reinforcement | 10 min | T4 |
| T5-05 | AI PM Interview Masterclass | Pattern E — Deep Reinforcement | 10 min | T5 |